## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Patient | Register Myself Using Mail Id | I Can Receive A Confirmation/Verification Mail | 1
1 | SB1/US2 | Patient | Receive A Confirmation Mail | I Can Access The Health Analysis Web Page | 1
1 | SB1/US3 | Patient | Login Into The System Using Mail Id And Password | I Can View/Edit My Profile | 1
1 | SB1/US4 | Patient | Modify The Account Password | I Can Keep My Account Secure | 1
1 | SB1/US5 | Doctor | Register Myself Using Mail Id | I Can Receive A Confirmation/Verification Mail | 1
1 | SB1/US6 | Doctor | Receive A Confirmation Mail | I Can Access The Health Analysis Web Page | 1
1 | SB1/US7 | Doctor | Login Into The System Using Mail Id And Password | I Can View/Edit My Profile | 1
1 | SB1/US8 | Doctor | Modify The Account Password | I Can Keep My Account Secure | 1
1 | SB1/US9 | Hospitals | Login Into The System Using Mail Id And Password | I Can View/Edit My Profile | 1
1 | SB1/US10 | Hospitals | Modify The Account Password | I Can Keep My Account Secure | 1
1 | SB1/US11 | Hospitals | Manage The Patient Activities | I Can Manage Patient Activities | 1
2 | SB2/US12 | Admin | purchase a Omega Device | I Can do coding in it | 2
2 | SB2/US13 | Admin | assemble the Omega for Sensor(Blood Pressure) | I Can Analyze the Performance | 2
2 | SB2/US14 | Admin | assemble the Omega for Sensor(Heart beat) | I Can Analyze the Performance | 2
2 | SB2/US15 | Admin | assemble the Omega for Sensor(Temperature) | I Can Analyze the Performance | 2
2 | SB2/US16 | Admin | assemble the Omega for Sensorglucose level) | I Can Analyze the Performance | 2
2 | SB2/US17 | Admin | Assemble the device | I Can make them in a very comfort and perfect way | 2
2 | SB2/US18 | Admin | do programming | I Can program to tranfer data to website | 2
3 | SB3/US19 | Patient | View The Report | I Can take precautions | 3
3 | SB3/US20 | Patient | View the daily report | I Can work accordingly | 3
3 | SB3/US21 | Patient | View My device problem | I Can Prevent The Mistakes | 3
3 | SB3/US22 | Patient | Download report | I Can show it wherever I want | 3
3 | SB3/US23 | Doctor | View The Report of patient | I Can analyse the patient | 3
3 | SB3/US24 | Doctor | View the daily report | I Can work accordingly and give prescriptions | 3
3 | SB3/US25 | Admin | Testing | I Can check my Device | 3
3 | SB3/US26 | Admin | Testing | I Can check the errors | 3
3 | SB3/US27 | Web Admin | receive data from omega | I Can view the reports | 3
3 | SB3/US28 | Web Admin | Download patient's reports | I Can Complete And Submit Them On Time | 3
3 | SB3/US29 | Web Admin | Fire Insert Queries | I Can Insert New Records In The Database | 3
3 | SB3/US30 | Web Admin | Fire Select Queries | I Can View The Records | 3
3 | SB3/US31 | Web Admin | Fire Update Queries | I Can Keep The Database Updated | 3
3 | SB3/US32 | Web Admin | Fire Delete Queries | I Can Remove Unwanted Data | 3
3 | SB3/US33 | Web Admin | Take Backup | I Can Save The Old Records In The Database For Future Use | 3
3 | SB3/US34 | Web Admin | Delete Backup | I Can Delete The Records Which Is Not Needed Any More | 3
3 | SB3/US35 | Web Admin | Generate Report | I Can review patient | 3
3 | SB3/US36 | Web Admin | Interpret data | I Can view data | 3
3 | SB3/US37 | Web Admin | Analysis data | I Can analysis data | 3
3 | SB3/US38 | Web Admin | Represent data | I Can represent data on graph | 3
3 | SB3/US39 | Hospitals | Create A List Of Patients using the device | I Can Create A List Of Patients using the device | 3
3 | SB3/US40 | Hospitals | Sending Information Through Emails | I Can Send Information Through Emails | 3
3 | SB3/US41 | Hospitals | Manage The Time Schedule For Consultation | I Can Manage The Time Schedule For Consultation | 3
3 | SB3/US42 | Hospitals | View The Details Of All Patients | I Can View All The Details Of Patients | 3
3 | SB3/US43 | Hospitals | Prepare Prescription For All Patients | I Can Prepare Prescription For All Patients | 3
3 | SB3/US44 | Hospitals | Update Time For Consultation | I Can Update Time For Consultation | 3
3 | SB3/US45 | Hospitals | Access To All Information Of Doctors On Duties | I Can Access The Information Of Doctors On Duties | 3
3 | SB3/US46 | Hospitals | Manage All Statistics And Data About Patients | I Can Manage All Statistics And Data About Patients | 3
3 | SB3/US47 | Hospitals | Generate reciept for consultation | I Can assisst doctor to prescribe medicines on the reciept | 3
4 | SB4/US48 | Patient | Discuss Among Other People | I Can Share My Experience | 4
4 | SB4/US49 | Doctor | Generate bill for Medicines prescribed | I Can take medicine charges | 4
4 | SB4/US50 | Doctor | Discuss Among Other People | I Can Share My Experience | 4
4 | SB4/US51 | Hospitals | Review And Feedback From Patients By Email | I Can Review And Feedback From Patients By Email | 4
4 | SB4/US52 | Hospitals | Generate bill for doctor's fees | I Can take consultation charges | 4
4 | SB4/US53 | Hospitals | Generate bill for Medicines prescribed | I Can take medicine charges | 4

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SB1/US1 | Register Myself Using Mail Id | SB1/D1/T1 | Designing of GUI
|  | SB1/D1/T2 | Validating user input at client level
|  | SB1/D1/T3 | Validating user input at server level
|  | SB1/D1/T4 | Connection with Database to insert the record.
|  | SB1/D1/T5 | Testing of the module on localhost and then on server.
SB1/US2 | Receive A Confirmation Mail | SB1/D2/T1 | Designing of Email(to be send)
|  | SB1/D2/T2 | Send Email via coding using the Mandrill App
|  | SB1/D2/T3 | Connection with database to update the status in the database.
|  | SB1/D2/T4 | Testing of the module on localhost and then on server.
SB1/US3 | Login Into The System Using Mail Id And Password | SB1/D3/T1 | Designing of GUI
|  | SB1/D3/T2 | Validating user input at client level
|  | SB1/D3/T3 | Validating user input at server level
|  | SB1/D3/T4 | Connection with Database to insert the record.
|  | SB1/D3/T5 | Testing of the module on localhost and then on server.
SB1/US4 | Modify The Account Password | SB1/D4/T1 | Designing of GUI
|  | SB1/D4/T2 | Validating user input at client level
|  | SB1/D4/T3 | Validating user input at server level
|  | SB1/D4/T4 | Connection with Database to insert the record.
|  | SB1/D4/T5 | Testing of the module on localhost and then on server.
SB1/US5 | Register Myself Using Mail Id | SB1/D5/T1 | Designing of GUI
|  | SB1/D5/T2 | Validating user input at client level
|  | SB1/D5/T3 | Validating user input at server level
|  | SB1/D5/T4 | Connection with Database to insert the record.
|  | SB1/D5/T5 | Testing of the module on localhost and then on server.
SB1/US6 | Receive A Confirmation Mail | SB1/D6/T1 | Designing of Email(to be send)
|  | SB1/D6/T2 | Send Email via coding using the Mandrill App
|  | SB1/D6/T3 | Connection with database to update the status in the database.
|  | SB1/D6/T4 | Testing of the module on localhost and then on server.
SB1/US7 | Login Into The System Using Mail Id And Password | SB1/D7/T2 | Designing of GUI
|  | SB1/D7/T2 | Validating user input at client level
|  | SB1/D7/T3 | Validating user input at server level
|  | SB1/D7/T4 | Connection with Database to insert the record.
|  | SB1/D7/T5 | Testing of the module on localhost and then on server.
SB1/US8 | Modify The Account Password | SB1/D8/T1 | Designing of GUI
|  | SB1/D8/T2 | Validating user input at client level
|  | SB1/D8/T3 | Validating user input at server level
|  | SB1/D8/T4 | Connection with Database to insert the record.
|  | SB1/D8/T5 | Testing of the module on localhost and then on server.
SB1/US9 | Login Into The System Using Mail Id And Password | SB1/D9/T1 | Designing of GUI
|  | SB1/D9/T2 | Validating user input at client level
|  | SB1/D9/T3 | Validating user input at server level
|  | SB1/D9/T4 | Connection with Database to insert the record.
|  | SB1/D9/T5 | Testing of the module on localhost and then on server.
SB1/US10 | Modify The Account Password | SB1/D10/T1 | Designing of GUI
|  | SB1/D10/T2 | Validating user input at client level
|  | SB1/D10/T3 | Validating user input at server level
|  | SB1/D10/T4 | Connection with Database to insert the record.
|  | SB1/D10/T5 | Testing of the module on localhost and then on server.
SB1/US11 | Manage The Patient Activities | SB1/D11/T1 | Designing of GUI
|  | SB1/D11/T2 | Validating user input at client level
|  | SB1/D11/T3 | Validating user input at server level
|  | SB1/D11/T4 | Connection with Database to insert the record.
|  | SB1/D11/T5 | Testing of the module on localhost and then on server.

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a patient I want to Register Myself Using Mail Id | Designing of GUI | 8
|  | Validating user input at client level | 4
|  | Validating user input at server level | 4
|  | Connection with Database to insert the record. | 8
|  | Testing of the module on localhost and then on server. | 4
2 | As a patient I want to Receive A Confirmation Mail | Designing of Email(to be send) | 2
|  | Send Email via coding using the Mandrill App | 4
|  | Connection with database to update the status in the database. | 4
|  | Testing of the module on localhost and then on server. | 4
3 | As a patient I want to Login Into The System Using Mail Id And Password | Designing of GUI | 8
|  | Validating user input at client level | 4
|  | Validating user input at server level | 4
|  | Connection with Database to insert the record. | 8
|  | Testing of the module on localhost and then on server. | 4
4 | As a patient I want to Modify The Account Password | Designing of GUI | 8
|  | Validating user input at client level | 4
|  | Validating user input at server level | 4 |  |  | 0
|  | Connection with Database to insert the record. | 8
|  | Testing of the module on localhost and then on server. | 4 |  |  | 0
5 | As a Doctor I want to Register Myself Using Mail Id | Designing of GUI | 8 |  |  | 0
|  | Validating user input at client level | 4 |  |  | 0
|  | Validating user input at server level | 4
|  | Connection with Database to insert the record. | 8
|  | Testing of the module on localhost and then on server. | 4
6 | As a Doctor I want to Receive A Confirmation Mail | Designing of Email(to be send) | 2
|  | Send Email via coding using the Mandrill App | 4
|  | Connection with database to update the status in the database. | 4
|  | Testing of the module on localhost and then on server. | 4
7 | As a Doctor I want to Login Into The System Using Mail Id And Password | Designing of GUI | 8
|  | Validating user input at client level | 4
|  | Validating user input at server level | 4
|  | Connection with Database to insert the record. | 8
|  | Testing of the module on localhost and then on server. | 4
8 | As a Doctor I want to Modify The Account Password | Designing of GUI | 8
|  | Validating user input at client level | 4
|  | Validating user input at server level | 4
|  | Connection with Database to insert the record. | 8
|  | Testing of the module on localhost and then on server. | 4
9 | As a Hospital Administrator I want to Login Into The System Using Mail Id And Password | Designing of GUI | 8
|  | Validating user input at client level | 4
|  | Validating user input at server level | 4
|  | Connection with Database to insert the record. | 8
|  | Testing of the module on localhost and then on server. | 4
10 | As a Hospital Administrator I want to Modify The Account Password | Designing of GUI | 8
|  | Validating user input at client level | 4
|  | Validating user input at server level | 4
|  | Connection with Database to insert the record. | 8
|  | Testing of the module on localhost and then on server. | 4
11 | As a Hospital Administrator I want to Manage The Patient Activities | Designing of GUI | 8
|  | Validating user input at client level | 4
|  | Validating user input at server level | 4
|  | Connection with Database to insert the record. | 8
|  | Testing of the module on localhost and then on server. | 4
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 180 | Tasks
2018-09-12 | 120 | 180
2018-09-11 | 80 | 180
2018-09-14 | 56 | 180
2018-09-16 | 15 | 180
2018-09-18 | 5 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SB2/US12 | As an Admin I want to purchase a Omega Device | SB2/D1/T1 | Search about the hardware setup
|  | SB2/D1/T2 | Search about components required
|  | SB2/D1/T3 | Purchase component from Market
|  | SB2/D1/T4 | Develop the hardware
SB2/US13 | As an Admin I want to assemble the Omega for Sensor(Blood Pressure) | SB2/D2/T1 | Search about the hardware setup
|  | SB2/D2/T2 | Purchase component from Market
|  | SB2/D2/T3 | Develop the hardware
SB2/US14 | As an Admin I want to assemble the Omega for Sensor(Heart beat) | SB2/D3/T1 | Search about the hardware setup
|  | SB2/D3/T2 | Purchase component from Market
|  | SB2/D3/T3 | Develop the hardware
SB2/US15 | As an Admin I want to assemble the Omega for Sensor(Temperature) | SB2/D4/T1 | Search about the hardware setup
|  | SB2/D4/T2 | Purchase component from Market
|  | SB2/D4/T3 | Develop the hardware
SB2/US16 | As an Admin I want to assemble the Omega for Sensor(glucose level) | SB2/D5/T1 | Search about the hardware setup
|  | SB2/D5/T2 | Purchase component from Market
|  | SB2/D5/T3 | Develop the hardware
SB2/US17 | As an Admin I want to Assemble the device | SB2/D6/T1 | Search about the hardware setup
|  | SB2/D6/T2 | Assemble all the sensors and omega
|  | SB2/D6/T3 | Develop the hardware
SB2/US18 | As an Admin I want to do programming | SB2/D7/T1 | coding of onscreen application
|  | SB2/D7/T2 | coding of onscreen application
|  | SB2/D7/T3 | Debug the code
|  | SB2/D7/T4 | Debug the code

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | purchase a Omega Device | Search about the hardware setup | 8
|  | Search about components required | 8
|  | Purchase component from Market | 60
|  | Develop the hardware | 8
2 | assemble the Omega for Sensor(Blood Pressure) | Search about the hardware setup | 12
|  | Purchase component from Market | 48
|  | Develop the hardware | 8
3 | assemble the Omega for Sensor(Heart beat) | Search about the hardware setup | 12
|  | Purchase component from Market | 48
|  | Develop the hardware | 8
4 | assemble the Omega for Sensor(Temperature) | Search about the hardware setup | 12
|  | Purchase component from Market | 48
|  | Develop the hardware | 8
5 | assemble the Omega for Sensor(glucose level) | Search about the hardware setup | 12
|  | Purchase component from Market | 48
|  | Develop the hardware | 8
6 | Assemble the device | Search about the hardware setup | 12
|  | Assemble all the sensors and omega | 12
|  | Develop the hardware | 12
7 | do programming | coding of onscreen application | 8
|  | coding of onscreen application | 8
|  | Debug the code | 4
|  | Debug the code | 4
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SB3/US19 | As a patient I want to View The Report | SB3/D1/T1 | login with the registered email id
|  | SB3/D1/T2 | view and analyse the report
SB3/US20 | As a patient I want to View the daily report | SB3/D2/T1 | login with the registered email id
|  | SB3/D2/T2 | view and analyse the report
SB3/US21 | As a patient I want to View My device problem | SB3/D3/T1 | use the device
|  | SB3/D3/T2 | observe the results
|  | SB3/D3/T3 | if problem found report to admin
SB3/US22 | As a patient I want to Download report | SB3/D4/T1 | login with the registered email id
|  | SB3/D4/T2 | download the report
SB3/US23 | As a doctor I want to View The Report of patient | SB3/D5/T1 | login with registered email id
|  | SB3/D5/T2 | select the patient associated
|  | SB3/D5/T3 | view the report of patient
SB3/US24 | As a doctor I want to View the daily report | SB3/D6/T1 | login with registered email id
|  | SB3/D6/T2 | select the patient associated
|  | SB3/D6/T3 | view the report of patient
SB3/US25 | As an admin I want to do Testing of device | SB3/D7/T1 | view the complaints posted by patients
|  | SB3/D7/T2 | test the device
|  | SB3/D7/T3 | modify the device
SB3/US26 | As an admin I want to do Testing of program | SB3/D8/T1 | view the complaints posted by patients
|  | SB3/D8/T2 | test the program
|  | SB3/D8/T3 | modify the program

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| As a patient I want to View The Report | login with the registered email id | 2
|  | view and analyse the report | 2
| As a patient I want to View the daily report | login with the registered email id | 2
|  | view and analyse the report | 2
| As a patient I want to View My device problem | use the device | 2
|  | observe the results | 2
|  | if problem found report to admin | 2
| As a patient I want to Download report | login with the registered email id | 2
|  | download the report | 2
| As a doctor I want to View The Report of patient | login with registered email id | 2
|  | select the patient associated | 2
|  | view the report of patient | 2
| As a doctor I want to View the daily report | login with registered email id | 2
|  | select the patient associated | 2
|  | view the report of patient | 2
| As an admin I want to do Testing of device | view the complaints posted by patients | 2
|  | test the device | 4
|  | modify the device | 4
| As an admin I want to do Testing of program | view the complaints posted by patients | 2
|  | test the program | 4
|  | modify the program | 4
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SB4/US48 | Discuss Among Other People | SB4/D1/T1 | share the device information
|  | SB4/D1/T2 | share the application information
SB4/US49 | Generate bill for Medicines prescribed | SB4/D2/T1 | analyse the patient problem
|  | SB4/D2/T2 | prescribe the medicine
|  | SB4/D2/T3 | generate bill for the prescription
SB4/US50 | Discuss Among Other People | SB4/D3/T1 | share the device information
|  | SB4/D3/T2 | share the application information
SB4/US51 | Review And Feedback From Patients By Email | SB4/D4/T1 | use the device
|  | SB4/D4/T2 | login by using registered email id
|  | SB4/D4/T3 | provide review and feedback
SB4/US52 | Generate bill for doctor's fees | SB4/D5/T1 | analyse the patient problem
|  | SB4/D5/T2 | prescribe the medicine
|  | SB4/D5/T3 | generate bill for the prescription
SB4/US53 | Generate bill for Medicines prescribed | SB4/D5/T1 | analyse the patient problem
|  | SB4/D5/T2 | prescribe the medicine
|  | SB4/D5/T3 | generate bill for the prescription

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| Discuss Among Other People | share the device information | 1
|  | share the application information | 1
| Generate bill for Medicines prescribed | analyse the patient problem | 1
|  | prescribe the medicine | 1
|  | generate bill for the prescription | 1
| Discuss Among Other People | share the device information | 1
|  | share the application information | 1
| Review And Feedback From Patients By Email | use the device | 2
|  | login by using registered email id | 2
|  | provide review and feedback | 2
| Generate bill for doctor's fees | analyse the patient problem | 1
|  | prescribe the medicine | 1
|  | generate bill for the prescription | 1
| Generate bill for Medicines prescribed | analyse the patient problem | 1
|  | prescribe the medicine | 1
|  | generate bill for the prescription | 1
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days